## Cover Sheet
IENG 366: | Engineering Management
HW 04: | Project Planning & Management
Submitted by: | Solution
Date:

## Questions & Data
Use the table at right to enter formulas to compute the planned duration [t (e)] and the variance of each of the activities. |  |  |  |  | Duration
| Activity | Resource | Predecessor(s) | Successor(s) | Optimistic | Most Likely | Pessimistic | t (e) | VAR | Slack
| A | a |  | B, C, D | 3 | 6 | 10 | 6.1667 | 1.3611 | 0
Then go to the Network tab and perform the forward pass to compute the early start and early finish for the network. Compute the Crtical Time for the network, then perform the backward pass and compute the late finish and late start for each activity. Then list the activities on the Critical Path.. | B | b | A | E, F | 5 | 8 | 12 | 8.1667 | 1.3611 | 0
| C | c | A | I, J | 4 | 6 | 9 | 6.1667 | 0.69444 | 13.1667
| D | d | A | G | 4 | 5 | 7 | 5.1667 | 0.25 | 12.3333
| E | a | B | H | 3 | 6 | 10 | 6.1667 | 1.3611 | 0
Return to the table at right and enter formulas to compute the slack time for each of the activities. Use the variance and t (e ) values of the critical path to compute the probability that the project can be finished within 65 days. (Use Normal Dist tab to look up z-statistic!) | F | b | B | I | 3 | 4 | 6 | 4.1667 | 0.25 | 7
| G | c | D | K | 4 | 8 | 13 | 8.1667 | 2.25 | 12.3333
| H | d | E | L | 6 | 13 | 21 | 13.1667 | 6.25 | 0
The probability of completing the project in 65 days or less if the expected time is 52.0 days and the variance is 15.94 days^2 is 99.9%. Note that only the Critical Path activities are used to find the expected time and variance. | I | a | C, F | L | 4 | 8 | 13 | 8.1667 | 2.25 | 7
| J | b | C | M, N | 4 | 5 | 7 | 5.1667 | 0.25 | 13.1667
| K | c | G | O | 4 | 8 | 13 | 8.1667 | 2.25 | 12.3333
| L | d | H, I | P | 4 | 8 | 13 | 8.1667 | 2.25 | 0
| M | a | J | P | 3 | 6 | 10 | 6.1667 | 1.3611 | 18.1667
Go to the Gantt Chart tab and use the fill tool to show the correct completion percentage (graphically) for activities E and F. Use the blue line for the current date to anwer the following questions: | N | b | J | P | 5 | 11 | 18 | 11.1667 | 4.6944 | 13.1667
| O | c | K | P | 1 | 2 | 2 | 1.8333 | 0.027778 | 12.3333
| P | d | L, M, N, O |  | 5 | 10 | 16 | 10.1667 | 3.3611 | 0
Which activites are currently behind schedule? | [6 empty] | Expected Time: | 52
Tasks B, D, E, and F are currently behind schedule. | [6 empty] | Variance: | 15.9444
|  | z = | 3.2557
|  | P(z) = | 0.99944
Which activites are currently ahead of schedule?
Tasks G, H, and I are currently ahead of schedule.
Which activity is currently scheduled to start?
Task J is currently scheduled to start.
Assuming that there are four people available to work on this project, and that each person works at the same rate and can perform any activity, can this project be back on schedule (or ahead) in five days? (Describe how)
Task G, H, and I are currently a total of 9.5 days ahead of schedule, and will require a total of 4.5 days more work to be exactly on schedule five days from now. Tasks B, D, E, and F are currently 7 days behind schedule and will require 1 additional day of work to be on schedule five days from now. The total of days of work needed to be on schedule in five days is: 4.5 + 7 + 1 +5 = 17.5 days, and if there are four people available to work for the five days, there are 5 x 4 = 20 days of labor available;so YES, many combinations of workers and tasks will suffice.

## Network
|  |  |  | 14.3333 | 20.5 | 20.5 | 33.6667
|  |  |  | E | 6.1667 | H | 13.1667
|  |  |  | 14.3333 | 20.5 | 20.5 | 33.6667
|  | 6.1667 | 14.3333 | 14.3333 | 18.5 | 18.5 | 26.6667 | 33.6667 | 41.8333 |  |  | Critical Time: | 52
|  | B | 8.1667 | F | 4.1667 | I | 8.1667 | L | 8.1667
|  | 6.1667 | 14.3333 | 21.3333 | 25.5 | 25.5 | 33.6667 | 33.6667 | 41.8333 |  |  | Critical Path: | A, B, E, H, L, P
0 | 6.1667 | 6.1667 | 12.3333 |  |  | 12.3333 | 17.5 | 17.5 | 23.6667 | 41.8333 | 52
A | 6.1667 | C | 6.1667 |  |  | J | 5.1667 | M | 6.1667 | P | 10.1667
0 | 6.1667 | 19.3333 | 25.5 |  |  | 25.5 | 30.6667 | 35.6667 | 41.8333 | 41.8333 | 52
|  | 6.1667 | 11.3333 | 11.3333 | 19.5 | 19.5 | 27.6667 | 17.5 | 28.6667
|  | D | 5.1667 | G | 8.1667 | K | 8.1667 | N | 11.1667
|  | 18.5 | 23.6667 | 23.6667 | 31.8333 | 31.8333 | 40 | 30.6667 | 41.8333
[8 empty] | 27.6667 | 29.5
[8 empty] | O | 1.8333
[8 empty] | 40 | 41.8333

## Gantt Chart
|  |  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Activity | Duration | Slack | % Comp
A | 6 | 0 | 100%
B | 8 | 0 | 75%
C | 6 | 13.1667 | 100%
D | 5 | 12.3333 | 80%
E | 6 | 0 | 50%
F | 4 | 7 | 50%
G | 8 | 12.3333 | 75%
H | 13 | 0 | 50%
I | 8 | 7 | 25%
J | 5 | 13.1667 | 0%
K | 8 | 12.3333 | 0%
L | 8 | 0 | 0%
M | 6 | 18.1667 | 0%
N | 12 | 13.1667 | 0%
O | 2 | 12.3333 | 0%
P | 10 | 0 | 0%

## Normal Dist
|  |  | Cumulative Area Under the Standard Normal Curve - |  |  |  |  | [f(z)]
z | 0 | 0.01 | 0.02 | 0.03 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.09 | Alpha | One-sided | Two-sided
0 | 0.5 | 0.50399 | 0.50798 | 0.51197 | 0.51595 | 0.51994 | 0.52392 | 0.5279 | 0.53188 | 0.53586 | Level (a) | z | z
0.1 | 0.53983 | 0.5438 | 0.54776 | 0.55172 | 0.55567 | 0.55962 | 0.56356 | 0.56749 | 0.57142 | 0.57535 | 0.1 | 1.2816 | 1.6449
0.2 | 0.57926 | 0.58317 | 0.58706 | 0.59095 | 0.59483 | 0.59871 | 0.60257 | 0.60642 | 0.61026 | 0.61409 | 0.05 | 1.6449 | 1.96
0.3 | 0.61791 | 0.62172 | 0.62552 | 0.6293 | 0.63307 | 0.63683 | 0.64058 | 0.64431 | 0.64803 | 0.65173 | 0.025 | 1.96 | 2.2414
0.4 | 0.65542 | 0.6591 | 0.66276 | 0.6664 | 0.67003 | 0.67364 | 0.67724 | 0.68082 | 0.68439 | 0.68793 | 0.01 | 2.3263 | 2.5758
0.5 | 0.69146 | 0.69497 | 0.69847 | 0.70194 | 0.7054 | 0.70884 | 0.71226 | 0.71566 | 0.71904 | 0.7224 | 0.005 | 2.5758 | 2.807
0.6 | 0.72575 | 0.72907 | 0.73237 | 0.73565 | 0.73891 | 0.74215 | 0.74537 | 0.74857 | 0.75175 | 0.7549 | 0.0025 | 2.807 | 3.0233
0.7 | 0.75804 | 0.76115 | 0.76424 | 0.7673 | 0.77035 | 0.77337 | 0.77637 | 0.77935 | 0.7823 | 0.78524 | 0.001 | 3.0902 | 3.2905
0.8 | 0.78814 | 0.79103 | 0.79389 | 0.79673 | 0.79955 | 0.80234 | 0.80511 | 0.80785 | 0.81057 | 0.81327
0.9 | 0.81594 | 0.81859 | 0.82121 | 0.82381 | 0.82639 | 0.82894 | 0.83147 | 0.83398 | 0.83646 | 0.83891 |  | m ± nσ | Area
1 | 0.84134 | 0.84375 | 0.84614 | 0.84849 | 0.85083 | 0.85314 | 0.85543 | 0.85769 | 0.85993 | 0.86214 |  | ±3σ | 0.9973
1.1 | 0.86433 | 0.8665 | 0.86864 | 0.87076 | 0.87286 | 0.87493 | 0.87698 | 0.879 | 0.881 | 0.88298 |  | ±2σ | 0.9545
1.2 | 0.88493 | 0.88686 | 0.88877 | 0.89065 | 0.89251 | 0.89435 | 0.89617 | 0.89796 | 0.89973 | 0.90147 |  | ±1σ | 0.68269
1.3 | 0.9032 | 0.9049 | 0.90658 | 0.90824 | 0.90988 | 0.91149 | 0.91309 | 0.91466 | 0.91621 | 0.91774
1.4 | 0.91924 | 0.92073 | 0.9222 | 0.92364 | 0.92507 | 0.92647 | 0.92785 | 0.92922 | 0.93056 | 0.93189
1.5 | 0.93319 | 0.93448 | 0.93574 | 0.93699 | 0.93822 | 0.93943 | 0.94062 | 0.94179 | 0.94295 | 0.94408
1.6 | 0.9452 | 0.9463 | 0.94738 | 0.94845 | 0.9495 | 0.95053 | 0.95154 | 0.95254 | 0.95352 | 0.95449
1.7 | 0.95543 | 0.95637 | 0.95728 | 0.95818 | 0.95907 | 0.95994 | 0.9608 | 0.96164 | 0.96246 | 0.96327
1.8 | 0.96407 | 0.96485 | 0.96562 | 0.96638 | 0.96712 | 0.96784 | 0.96856 | 0.96926 | 0.96995 | 0.97062
1.9 | 0.97128 | 0.97193 | 0.97257 | 0.9732 | 0.97381 | 0.97441 | 0.975 | 0.97558 | 0.97615 | 0.9767
2 | 0.97725 | 0.97778 | 0.97831 | 0.97882 | 0.97932 | 0.97982 | 0.9803 | 0.98077 | 0.98124 | 0.98169
2.1 | 0.98214 | 0.98257 | 0.983 | 0.98341 | 0.98382 | 0.98422 | 0.98461 | 0.985 | 0.98537 | 0.98574
2.2 | 0.9861 | 0.98645 | 0.98679 | 0.98713 | 0.98745 | 0.98778 | 0.98809 | 0.9884 | 0.9887 | 0.98899
2.3 | 0.98928 | 0.98956 | 0.98983 | 0.9901 | 0.99036 | 0.99061 | 0.99086 | 0.99111 | 0.99134 | 0.99158
2.4 | 0.9918 | 0.99202 | 0.99224 | 0.99245 | 0.99266 | 0.99286 | 0.99305 | 0.99324 | 0.99343 | 0.99361
2.5 | 0.99379 | 0.99396 | 0.99413 | 0.9943 | 0.99446 | 0.99461 | 0.99477 | 0.99492 | 0.99506 | 0.9952
2.6 | 0.99534 | 0.99547 | 0.9956 | 0.99573 | 0.99585 | 0.99598 | 0.99609 | 0.99621 | 0.99632 | 0.99643
2.7 | 0.99653 | 0.99664 | 0.99674 | 0.99683 | 0.99693 | 0.99702 | 0.99711 | 0.9972 | 0.99728 | 0.99736
2.8 | 0.99744 | 0.99752 | 0.9976 | 0.99767 | 0.99774 | 0.99781 | 0.99788 | 0.99795 | 0.99801 | 0.99807
2.9 | 0.99813 | 0.99819 | 0.99825 | 0.99831 | 0.99836 | 0.99841 | 0.99846 | 0.99851 | 0.99856 | 0.99861
3 | 0.99865 | 0.99869 | 0.99874 | 0.99878 | 0.99882 | 0.99886 | 0.99889 | 0.99893 | 0.99896 | 0.999
3.1 | 0.99903 | 0.99906 | 0.9991 | 0.99913 | 0.99916 | 0.99918 | 0.99921 | 0.99924 | 0.99926 | 0.99929
3.2 | 0.99931 | 0.99934 | 0.99936 | 0.99938 | 0.9994 | 0.99942 | 0.99944 | 0.99946 | 0.99948 | 0.9995
3.3 | 0.99952 | 0.99953 | 0.99955 | 0.99957 | 0.99958 | 0.9996 | 0.99961 | 0.99962 | 0.99964 | 0.99965
3.4 | 0.99966 | 0.99968 | 0.99969 | 0.9997 | 0.99971 | 0.99972 | 0.99973 | 0.99974 | 0.99975 | 0.99976
3.5 | 0.99977 | 0.99978 | 0.99978 | 0.99979 | 0.9998 | 0.99981 | 0.99981 | 0.99982 | 0.99983 | 0.99983
3.6 | 0.99984 | 0.99985 | 0.99985 | 0.99986 | 0.99986 | 0.99987 | 0.99987 | 0.99988 | 0.99988 | 0.99989
3.7 | 0.99989 | 0.9999 | 0.9999 | 0.9999 | 0.99991 | 0.99991 | 0.99992 | 0.99992 | 0.99992 | 0.99992
3.8 | 0.99993 | 0.99993 | 0.99993 | 0.99994 | 0.99994 | 0.99994 | 0.99994 | 0.99995 | 0.99995 | 0.99995
3.9 | 0.99995 | 0.99995 | 0.99996 | 0.99996 | 0.99996 | 0.99996 | 0.99996 | 0.99996 | 0.99997 | 0.99997
4 | 0.99997 | 0.99997 | 0.99997 | 0.99997 | 0.99997 | 0.99997 | 0.99998 | 0.99998 | 0.99998 | 0.99998
4.1 | 0.99998 | 0.99998 | 0.99998 | 0.99998 | 0.99998 | 0.99998 | 0.99998 | 0.99998 | 0.99999 | 0.99999
4.2 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999
4.3 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999
4.4 | 0.99999 | 0.99999 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1