## Cover Sheet
IENG 366: | Engineering Management
HW 04: | Project Planning & Management
Submitted by:
Date:

## Questions & Data
Use the table at right to enter formulas to compute the planned duration [t (e)] and the variance of each of the activities. |  |  |  |  | Duration
| Activity | Resource | Predecessor(s) | Successor(s) | Optimistic | Most Likely | Pessimistic | t (e) | VAR | Slack
| A | a |  | B, C, D | 3 | 6 | 10
Then go to the Network tab and perform the forward pass to compute the early start and early finish for the network. Compute the Crtical Time for the network, then perform the backward pass and compute the late finish and late start for each activity. Then list the activities on the Critical Path.. | B | b | A | E, F | 5 | 8 | 12
| C | c | A | I, J | 4 | 6 | 9
| D | d | A | G | 4 | 5 | 7
| E | a | B | H | 3 | 6 | 10
Return to the table at right and enter formulas to compute the slack time for each of the activities. Use the variance and t (e ) values of the critical path to compute the probability that the project can be finished within 65 days. (Use Normal Dist tab to look up z-statistic!) | F | b | B | I | 3 | 4 | 6
| G | c | D | K | 4 | 8 | 13
| H | d | E | L | 6 | 13 | 21
Put your answer to the question immediately above in this box. | I | a | C, F | L | 4 | 8 | 13
| J | b | C | M, N | 4 | 5 | 7
| K | c | G | O | 4 | 8 | 13
| L | d | H, I | P | 4 | 8 | 13
| M | a | J | P | 3 | 6 | 10
Go to the Gantt Chart tab and use the fill tool to show the correct completion percentage (graphically) for activities E and F. Use the blue line for the current date to anwer the following questions: | N | b | J | P | 5 | 11 | 18
| O | c | K | P | 1 | 2 | 2
| P | d | L, M, N, O |  | 5 | 10 | 16
Which activites are currently behind schedule?
Put your answer to the question immediately above in this box.
Which activites are currently ahead of schedule?
Put your answer to the question immediately above in this box.
Which activity is currently scheduled to start?
Put your answer to the question immediately above in this box.
Assuming that there are four people available to work on this project, and that each person works at the same rate and can perform any activity, can this project be back on schedule (or ahead) in five days? (Describe how)
Put your answer to the question immediately above in this box.

## Network
|  |  |  | E | 0 | H | 0
|  | 0 | [9 empty] | Critical Time:
|  | B | 0 | F | 0 | I | 0 | L | 0
Critical Path:
0 | 0 | 0
A | 0 | C | 0 |  |  | J | 0 | M | 0 | P | 0
0
0
|  | D | 0 | G | 0 | K | 0 | N | 0
[8 empty] | O | 0

## Gantt Chart
|  |  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Activity | Duration | Slack | % Comp
A | 6 | 0 | 100%
B | 8 | 0 | 75%
C | 6 | 0 | 100%
D | 5 | 0 | 80%
E | 6 | 0 | 50%
F | 4 | 0 | 50%
G | 8 | 0 | 75%
H | 13 | 0 | 50%
I | 8 | 0 | 25%
J | 5 | 0 | 0%
K | 8 | 0 | 0%
L | 8 | 0 | 0%
M | 6 | 0 | 0%
N | 12 | 0 | 0%
O | 2 | 0 | 0%
P | 10 | 0 | 0%

## Normal Dist
|  |  | Cumulative Area Under the Standard Normal Curve - |  |  |  |  | [f(z)]
z | 0 | 0.01 | 0.02 | 0.03 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.09 | Alpha | One-sided | Two-sided
0 | 0.5 | 0.50399 | 0.50798 | 0.51197 | 0.51595 | 0.51994 | 0.52392 | 0.5279 | 0.53188 | 0.53586 | Level (a) | z | z
0.1 | 0.53983 | 0.5438 | 0.54776 | 0.55172 | 0.55567 | 0.55962 | 0.56356 | 0.56749 | 0.57142 | 0.57535 | 0.1 | 1.2816 | 1.6449
0.2 | 0.57926 | 0.58317 | 0.58706 | 0.59095 | 0.59483 | 0.59871 | 0.60257 | 0.60642 | 0.61026 | 0.61409 | 0.05 | 1.6449 | 1.96
0.3 | 0.61791 | 0.62172 | 0.62552 | 0.6293 | 0.63307 | 0.63683 | 0.64058 | 0.64431 | 0.64803 | 0.65173 | 0.025 | 1.96 | 2.2414
0.4 | 0.65542 | 0.6591 | 0.66276 | 0.6664 | 0.67003 | 0.67364 | 0.67724 | 0.68082 | 0.68439 | 0.68793 | 0.01 | 2.3263 | 2.5758
0.5 | 0.69146 | 0.69497 | 0.69847 | 0.70194 | 0.7054 | 0.70884 | 0.71226 | 0.71566 | 0.71904 | 0.7224 | 0.005 | 2.5758 | 2.807
0.6 | 0.72575 | 0.72907 | 0.73237 | 0.73565 | 0.73891 | 0.74215 | 0.74537 | 0.74857 | 0.75175 | 0.7549 | 0.0025 | 2.807 | 3.0233
0.7 | 0.75804 | 0.76115 | 0.76424 | 0.7673 | 0.77035 | 0.77337 | 0.77637 | 0.77935 | 0.7823 | 0.78524 | 0.001 | 3.0902 | 3.2905
0.8 | 0.78814 | 0.79103 | 0.79389 | 0.79673 | 0.79955 | 0.80234 | 0.80511 | 0.80785 | 0.81057 | 0.81327
0.9 | 0.81594 | 0.81859 | 0.82121 | 0.82381 | 0.82639 | 0.82894 | 0.83147 | 0.83398 | 0.83646 | 0.83891 |  | m ± nσ | Area
1 | 0.84134 | 0.84375 | 0.84614 | 0.84849 | 0.85083 | 0.85314 | 0.85543 | 0.85769 | 0.85993 | 0.86214 |  | ±3σ | 0.9973
1.1 | 0.86433 | 0.8665 | 0.86864 | 0.87076 | 0.87286 | 0.87493 | 0.87698 | 0.879 | 0.881 | 0.88298 |  | ±2σ | 0.9545
1.2 | 0.88493 | 0.88686 | 0.88877 | 0.89065 | 0.89251 | 0.89435 | 0.89617 | 0.89796 | 0.89973 | 0.90147 |  | ±1σ | 0.68269
1.3 | 0.9032 | 0.9049 | 0.90658 | 0.90824 | 0.90988 | 0.91149 | 0.91309 | 0.91466 | 0.91621 | 0.91774
1.4 | 0.91924 | 0.92073 | 0.9222 | 0.92364 | 0.92507 | 0.92647 | 0.92785 | 0.92922 | 0.93056 | 0.93189
1.5 | 0.93319 | 0.93448 | 0.93574 | 0.93699 | 0.93822 | 0.93943 | 0.94062 | 0.94179 | 0.94295 | 0.94408
1.6 | 0.9452 | 0.9463 | 0.94738 | 0.94845 | 0.9495 | 0.95053 | 0.95154 | 0.95254 | 0.95352 | 0.95449
1.7 | 0.95543 | 0.95637 | 0.95728 | 0.95818 | 0.95907 | 0.95994 | 0.9608 | 0.96164 | 0.96246 | 0.96327
1.8 | 0.96407 | 0.96485 | 0.96562 | 0.96638 | 0.96712 | 0.96784 | 0.96856 | 0.96926 | 0.96995 | 0.97062
1.9 | 0.97128 | 0.97193 | 0.97257 | 0.9732 | 0.97381 | 0.97441 | 0.975 | 0.97558 | 0.97615 | 0.9767
2 | 0.97725 | 0.97778 | 0.97831 | 0.97882 | 0.97932 | 0.97982 | 0.9803 | 0.98077 | 0.98124 | 0.98169
2.1 | 0.98214 | 0.98257 | 0.983 | 0.98341 | 0.98382 | 0.98422 | 0.98461 | 0.985 | 0.98537 | 0.98574
2.2 | 0.9861 | 0.98645 | 0.98679 | 0.98713 | 0.98745 | 0.98778 | 0.98809 | 0.9884 | 0.9887 | 0.98899
2.3 | 0.98928 | 0.98956 | 0.98983 | 0.9901 | 0.99036 | 0.99061 | 0.99086 | 0.99111 | 0.99134 | 0.99158
2.4 | 0.9918 | 0.99202 | 0.99224 | 0.99245 | 0.99266 | 0.99286 | 0.99305 | 0.99324 | 0.99343 | 0.99361
2.5 | 0.99379 | 0.99396 | 0.99413 | 0.9943 | 0.99446 | 0.99461 | 0.99477 | 0.99492 | 0.99506 | 0.9952
2.6 | 0.99534 | 0.99547 | 0.9956 | 0.99573 | 0.99585 | 0.99598 | 0.99609 | 0.99621 | 0.99632 | 0.99643
2.7 | 0.99653 | 0.99664 | 0.99674 | 0.99683 | 0.99693 | 0.99702 | 0.99711 | 0.9972 | 0.99728 | 0.99736
2.8 | 0.99744 | 0.99752 | 0.9976 | 0.99767 | 0.99774 | 0.99781 | 0.99788 | 0.99795 | 0.99801 | 0.99807
2.9 | 0.99813 | 0.99819 | 0.99825 | 0.99831 | 0.99836 | 0.99841 | 0.99846 | 0.99851 | 0.99856 | 0.99861
3 | 0.99865 | 0.99869 | 0.99874 | 0.99878 | 0.99882 | 0.99886 | 0.99889 | 0.99893 | 0.99896 | 0.999
3.1 | 0.99903 | 0.99906 | 0.9991 | 0.99913 | 0.99916 | 0.99918 | 0.99921 | 0.99924 | 0.99926 | 0.99929
3.2 | 0.99931 | 0.99934 | 0.99936 | 0.99938 | 0.9994 | 0.99942 | 0.99944 | 0.99946 | 0.99948 | 0.9995
3.3 | 0.99952 | 0.99953 | 0.99955 | 0.99957 | 0.99958 | 0.9996 | 0.99961 | 0.99962 | 0.99964 | 0.99965
3.4 | 0.99966 | 0.99968 | 0.99969 | 0.9997 | 0.99971 | 0.99972 | 0.99973 | 0.99974 | 0.99975 | 0.99976
3.5 | 0.99977 | 0.99978 | 0.99978 | 0.99979 | 0.9998 | 0.99981 | 0.99981 | 0.99982 | 0.99983 | 0.99983
3.6 | 0.99984 | 0.99985 | 0.99985 | 0.99986 | 0.99986 | 0.99987 | 0.99987 | 0.99988 | 0.99988 | 0.99989
3.7 | 0.99989 | 0.9999 | 0.9999 | 0.9999 | 0.99991 | 0.99991 | 0.99992 | 0.99992 | 0.99992 | 0.99992
3.8 | 0.99993 | 0.99993 | 0.99993 | 0.99994 | 0.99994 | 0.99994 | 0.99994 | 0.99995 | 0.99995 | 0.99995
3.9 | 0.99995 | 0.99995 | 0.99996 | 0.99996 | 0.99996 | 0.99996 | 0.99996 | 0.99996 | 0.99997 | 0.99997
4 | 0.99997 | 0.99997 | 0.99997 | 0.99997 | 0.99997 | 0.99997 | 0.99998 | 0.99998 | 0.99998 | 0.99998
4.1 | 0.99998 | 0.99998 | 0.99998 | 0.99998 | 0.99998 | 0.99998 | 0.99998 | 0.99998 | 0.99999 | 0.99999
4.2 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999
4.3 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999 | 0.99999
4.4 | 0.99999 | 0.99999 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1