## Cover Sheet
IENG 366: | Engineering Management
HW 05: | Project Costs Under Normal and Crash Efforts
Submitted by: | Solution
Date:

## Questions & Data
Use the table at right to enter formulas to compute the Slope and the Max Crash Time of each of the activities. Highlight the cell under the Activity heading that form the Critical Path with a red background. |  |  | Network Information |  | Duration | [5 empty] | Normal | Normal | Crash | Crash |  | Max Crash | 48 Day | 48 Day | Max | Max
| Activity | Resource | Predecessor(s) | Successor(s) | Optimistic | Most Likely | Pessimistic | t (e) | VAR | Slack | Time | Cost | Time | Cost | Slope | Time | Crash Time | Add Cost | Crash Time | Add Cost
| A | a |  | B, C, D | 3 | 6 | 10 | 7 | 1.3611 | 0 | 7 | 77 | 7 |  |  | 0 |  | 0 |  | 0
Use the table at right and enter formulas to compute the Normal Total Time and the Normal Total Cost from the values on the table. Summarize the Normal Total Time, Normal Total Cost, and critical path in the box below: | B | b | A | E, F | 5 | 8 | 12 | 9 | 1.3611 | 0 | 9 | 51 | 7 | 86 | 17.5 | 2 |  | 0 | 2 | 35
| C | c | A | I, J | 4 | 6 | 9 | 7 | 0.69444 | 1 | 7 | 95 | 5 | 108 | 6.5 | 2 |  | 0 |  | 0
| D | d | A | G | 4 | 5 | 7 | 6 | 0.25 | 0 | 6 | 88 | 5 | 104 | 16 | 1 |  | 0 |  | 0
The Normal Total Time is the same as the Critical Time: 57. The Normal Total Cost is the sum of the Normal Times for all the activities: $1,481. The Critical Path is A, B, E, H, L, P. | E | a | B | H | 3 | 6 | 10 | 7 | 1.3611 | 0 | 7 | 111 | 3 | 116 | 1.25 | 4 | 3 | 3.75 | 3 | 3.75
| F | b | B | I | 3 | 4 | 6 | 5 | 0.25 | 0 | 5 | 86 | 2 | 103 | 5.6667 | 3 |  | 0 | 1 | 5.6667
| G | c | D | K | 4 | 8 | 13 | 9 | 2.25 | 0 | 9 | 99 | 7 | 110 | 5.5 | 2 |  | 0 |  | 0
| H | d | E | L | 6 | 13 | 21 | 14 | 6.25 | 0 | 14 | 114 | 10 | 117 | 0.75 | 4 | 4 | 3 | 4 | 3
| I | a | C, F | L | 4 | 8 | 13 | 9 | 2.25 | 0 | 9 | 77 | 5 | 120 | 10.75 | 4 |  | 0 |  | 0
Assume that the project must be completed in 48 days. Which tasks must be crashed in order to accomplish this task at the lowest cost, and what is that lowest cost method? Summarize your answers in the box below, and remember to list which activities (and how many days) must be crashed: | J | b | C | M, N | 4 | 5 | 7 | 6 | 0.25 | 1 | 6 | 96 | 4 | 108 | 6 | 2 |  | 0 |  | 0
| K | c | G | O | 4 | 8 | 13 | 9 | 2.25 | 0 | 9 | 106 | 6 | 113 | 2.3333 | 3 |  | 0 |  | 0
| L | d | H, I | P | 4 | 8 | 13 | 9 | 2.25 | 0 | 9 | 101 | 6 | 111 | 3.3333 | 3 | 2 | 6.6667 | 3 | 10
The 48 Crash Cost will be $ 1,494, and the Critical Activities will add two more to the Critical Path: A, B, E, H, L, P, H, I. We get down to 48 by triming 9 periods from the Critical Pat. We select which activities by looking at the lowest cost Slope and the Max Crash Time constraint. In this case, we trim 4 from Activity H at $0.75 each, then trim 3 from E at $1.25 each, then trim 2 from L at 3.33 each. The Crash Cost increases from the Normal Total Cost by adding the trimmed days times the Slope for each of the trimmed activities. | M | a | J | P | 3 | 6 | 10 | 7 | 1.3611 | 6 | 7 | 114 | 3 | 117 | 0.75 | 4 |  | 0 |  | 0
| N | b | J | P | 5 | 11 | 18 | 12 | 4.6944 | 1 | 12 | 77 | 12 |  |  | 0 |  | 0 |  | 0
| O | c | K | P | 1 | 2 | 2 | 2 | 0.027778 | 0 | 2 | 93 | 1 | 107 | 14 | 1 |  | 0 |  | 0
| P | d | L, M, N, O |  | 5 | 10 | 16 | 11 | 3.3611 | 0 | 11 | 96 | 9 | 108 | 6 | 2 |  | 0 | 2 | 12
[17 empty] | 9 | 13.4167 | 15 | 69.4167
[11 empty] | Normal Total Time: | 57
What is the minimum time required to complete the project? | [7 empty] | Time: Normal Total Cost:; Cost: 1481
The minimum time is 42, at which point all of the Max Crash Time on the original Critical Path is used. Trying to trim an additional day from the Critical Path would violate the Max Crash Time constraint. | [7 empty] | Time: Critical Activities:; Cost: A, B, E, H, L, P
[11 empty] | 48 Crash Time: | 48
Go to the Network Tab and enter the minimum time in the Critical Time cell. Return to the table at right and highlight which activities also join the Critical Path(s) using a blue backround (as before). Summarize below: | [7 empty] | Time: 48 Crash Cost:; Cost: 1494.4167
[11 empty] | Critical Activities: | A, B, E, H, L, P, F, I
In trimming the Critical Path time further, more Activities join the Critical Path: D, G, K, and O join the other critical activities.
[11 empty] | Max Crash Time: | 42 |  |  | 15
[11 empty] | Max Crash Cost: | 1550.4167
Use the values in the table at right to enter a formula for the Max Crash Cost (cost to minimize the total time). Summarize the minimum time cost for the project below: | [7 empty] | Time: Critical Activities:; Cost: A, B, E, H, L, P, F, I, D, G, K, O
In adding the addition critical activities and finding the minimum cost crash cost, the Max Crash Cost becomes $1,550 to complete the project in the minimal time.

## Network
|  |  |  | 14 | 17 | 17 | 27
|  |  |  | E | 3 | H | 10
|  |  |  | 14 | 17 | 17 | 27
|  | 7 | 14 | 14 | 18 | 18 | 27 | 27 | 33 |  |  | Critical Time: | 42
|  | B | 7 | F | 4 | I | 9 | L | 6
|  | 7 | 14 | 14 | 18 | 18 | 27 | 27 | 33 |  |  | Critical Path:
0 | 7 | 7 | 14 |  |  | 14 | 20 | 20 | 27 | 33 | 42
A | 7 | C | 7 |  |  | J | 6 | M | 7 | P | 9
0 | 7 | 8 | 15 |  |  | 15 | 21 | 26 | 33 | 33 | 42
|  | 7 | 13 | 13 | 22 | 22 | 31 | 20 | 32
|  | D | 6 | G | 9 | K | 9 | N | 12
|  | 7 | 13 | 13 | 22 | 22 | 31 | 21 | 33
[8 empty] | 31 | 33
[8 empty] | O | 2
[8 empty] | 31 | 33