## Cover Sheet
IENG 366: | Engineering Management
HW 05: | Project Costs Under Normal and Crash Efforts
Submitted by:
Date:

## Questions & Data
Use the table at right to enter formulas to compute the Slope and the Max Crash Time of each of the activities. Highlight the cell under the Activity heading that form the Critical Path with a red background. |  |  | Network Information |  | Duration | [5 empty] | Normal | Normal | Crash | Crash |  | Max Crash
| Activity | Resource | Predecessor(s) | Successor(s) | Optimistic | Most Likely | Pessimistic | t (e) | VAR | Slack | Time | Cost | Time | Cost | Slope | Time
| A | a |  | B, C, D | 3 | 6 | 10 | 7 | 1.3611 | 0 | 7 | 77 | 7
Use the table at right and enter formulas to compute the Normal Total Time and the Normal Total Cost from the values on the table. Summarize the Normal Total Time, Normal Total Cost, and critical path in the box below: | B | b | A | E, F | 5 | 8 | 12 | 9 | 1.3611 | 0 | 9 | 51 | 7 | 86
| C | c | A | I, J | 4 | 6 | 9 | 7 | 0.69444 | 14 | 7 | 95 | 5 | 108
| D | d | A | G | 4 | 5 | 7 | 6 | 0.25 | 13 | 6 | 88 | 5 | 104
Put your answer to the question immediately above in this box. | E | a | B | H | 3 | 6 | 10 | 7 | 1.3611 | 0 | 7 | 111 | 3 | 116
| F | b | B | I | 3 | 4 | 6 | 5 | 0.25 | 7 | 5 | 86 | 2 | 103
| G | c | D | K | 4 | 8 | 13 | 9 | 2.25 | 13 | 9 | 99 | 7 | 110
| H | d | E | L | 6 | 13 | 21 | 14 | 6.25 | 0 | 14 | 114 | 10 | 117
| I | a | C, F | L | 4 | 8 | 13 | 9 | 2.25 | 7 | 9 | 77 | 5 | 120
Assume that the project must be completed in 48 days. Which tasks must be crashed in order to accomlish this task at the lowest cost, and what is that lowest cost method? Summarize your answers in the box below, and remember to list which activities (and how many days) must be crashed: | J | b | C | M, N | 4 | 5 | 7 | 6 | 0.25 | 14 | 6 | 96 | 4 | 108
| K | c | G | O | 4 | 8 | 13 | 9 | 2.25 | 13 | 9 | 106 | 6 | 113
| L | d | H, I | P | 4 | 8 | 13 | 9 | 2.25 | 0 | 9 | 101 | 6 | 111
Put your answer to the question immediately above in this box. | M | a | J | P | 3 | 6 | 10 | 7 | 1.3611 | 19 | 7 | 114 | 3 | 117
| N | b | J | P | 5 | 11 | 18 | 12 | 4.6944 | 14 | 12 | 77 | 12
| O | c | K | P | 1 | 2 | 2 | 2 | 0.027778 | 13 | 2 | 93 | 1 | 107
| P | d | L, M, N, O |  | 5 | 10 | 16 | 11 | 3.3611 | 0 | 11 | 96 | 9 | 108
Normal Total Time:
What is the minimum time required to complete the project? | [7 empty] | Time: Normal Total Cost:
Put your answer to the question immediately above in this box. | [7 empty] | Time: Critical Activities:
48 Crash Time:
Go to the Network Tab and enter the minimum time in the Critical Time cell. Return to the table at right and highlight which activities also join the Critical Path(s) using a blue backround (as before). Summarize below: | [7 empty] | Time: 48 Crash Cost:
Critical Activities:
Put your answer to the question immediately above in this box.
Max Crash Time:
Max Crash Cost:
Use the values in the table at right to enter a formula for the Max Crash Cost (cost to minimize the total time). Summarize the minimum time cost for the project below: | [7 empty] | Time: Critical Activities:
Put your answer to the question immediately above in this box.

## Network
|  |  |  | 16 | 23 | 23 | 37
|  |  |  | E | 7 | H | 14
|  |  |  | 16 | 23 | 23 | 37
|  | 7 | 16 | 16 | 21 | 21 | 30 | 37 | 46 |  |  | Critical Time: | 57
|  | B | 9 | F | 5 | I | 9 | L | 9
|  | 7 | 16 | 23 | 28 | 28 | 37 | 37 | 46 |  |  | Critical Path:
0 | 7 | 7 | 14 |  |  | 14 | 20 | 20 | 27 | 46 | 57
A | 7 | C | 7 |  |  | J | 6 | M | 7 | P | 11
0 | 7 | 21 | 28 |  |  | 28 | 34 | 39 | 46 | 46 | 57
|  | 7 | 13 | 13 | 22 | 22 | 31 | 20 | 32
|  | D | 6 | G | 9 | K | 9 | N | 12
|  | 20 | 26 | 26 | 35 | 35 | 44 | 34 | 46
[8 empty] | 31 | 33
[8 empty] | O | 2
[8 empty] | 44 | 46